## Sheet1
No | Nomor Nodin RFS/RFI | Tanggal nodin RFS/RFI | Subject | Status | Status RFC/ITR | Start FUT | FUT Done | Nomor Nodin RFC/ITR | Tanggal Nodin RFC/ITR | Subject Nodin RFC/ITR | Aging Nodin Dev - FUT Done | Aging Start FUT - Tgl RFC | Requestor | PIC Dev | Divisi | Remarks | Jml Test Case | Type | Nodin BO | Judul Nodin BO FU ke RPA | Tanggal Nodin BO | Business Owner | Sender Tittle Nodin BO | Sender Name Nodin BO | Standard/Normal Changes | BAU/Project | Service (Combo, Data, DLS, VAS, Etc) | Brand (All, Postpaid, Prepaid) | PIC Tester 1 | PIC Tester 2 | PIC Tester 3 | PIC Tester 4 | PIC Tester 5 | Testing Method | Tools Name | Sigos Automation | Prima Automation | FUT Simulator | Postman Simulator | Cetho Automation | Katalon Automation | Aging | Aging_Inspection | AgingStatus | Mark | Next Action | PIC | OnGoing_FUT | OnGoing_Inspection | Day | Month | BO Request | Year | Month Convert | Column1 | Column2
1 | 0001/MK.05/BE-23/I/2023 | 2023-05-02 | Pemberitahuan Ready for Service (RFS) Telkomsel Orbit CVM Winback & Prevention Revamp (PUMA Offer Adjustment) | DONE | OK with Notes | 2023-12-02 | 2023-01-05 | 0009/MK.05/BE-05/I/2023 | 2023-01-05 | Status Kesiapan Komersial (RFC) Telkomsel Orbit CVM Winback & Prevention Revamp (PUMA Offer Adjustment) (0001/MK.05/BE-23/I/2023) | 3 | 3 | Mgr. Home and Bundling Development | Mohamad Helda Baskoro Murdianto | #REF! | Beberapa paket dilakukan pengetesan dengan FUT Simulator. Disarankan untuk dilakukan proses inspection secara end2end ketika live, khususnya pembelian real dengan non-pulsa, gift, maupun omni channel. | 498 | RFS | 3372/IS.06/EN-01/IX/2022 | Permohonan Support untuk Penyesuaian Tarif CVM Telkomsel Orbit di Region Puma | 2022-09-26 | Bundling | Head of Home LTE Marketing | Lemen Koh Thong Lin | Standard | BAU | Bundling | All | Susi Sunarsih | Anisa Harasti |  |  |  | Partially Automation | (FUT Simulator) |  |  | 3 |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!